## Sheet1
A Helping Hand - Worklog (Ahan Debray)
Date | Day of Internship | Time | Activity/Task | Description of Activity/Task | Feedback from Supervisor | Reflection |  |  | Progress And Improvements | Focus Points For next Meeting | Tasks Till Next Meeting
[6 empty] | What | So What | Now What
2021-11-05 | Day 1 | 9:30AM | Welcome to Induction | This was a welcome to Induction day where the different aspects of the FreelancingHUB and related topics were presented and internship structure explained. | N/A | I was able to contribute and take part in the tasks but I remained in the background for the majority of the first half of the Activity | This clearly highlights one of the regions I will need to work on during the project and beyond | I plan on improving on this point in upcoming working days by interacting more and speaking clearly. | I was able to identify one area that required improvement | Conciously try to make more of a contribution to the discussion. | N/A
|  | 10:05AM | Scavenger Hunt | Scavenger Hunt was the first activity for the day. This was where I was introduced to my team. It was a team building exercise that required us to work together on multiple tasks.
|  | 11:00AM - 12:10PM | Past Student Experience / Professor Dineli Mather / Work Readiness | This Section of time was spent on listening to the experience of past students of various different projects, Professor Dineli Mather on graduate employment and best practives and Work Readiness
|  | 1:00PM | Design Thinking by Mary Phillips | This part of the day was a short introduction and explanation of what design thinking is, how it can be implemented to different problems and why to try and integrate it.
|  | 2:10PM | MS Teams / Zoom / Office Suite Guide by Michelle Howard | This was a basic guide and introduction to the different technologies that will be utilised throught the project.
|  | 2:40PM | Meeting With AHH Team | This was the final activity for the day where the project was discussed at a high level, a general timeline was set and introductions were made.
2021-11-09 | Day 2 | 9:00AM | Introduction, Roles & FreelancingHUB Agreement Signing | This was the first day working on the project. During this initial portion introductions were made in more detail describing background and role preferances. We also filled out and signed the FreelancingHUB agreeement. | N/A | I tried to be more active, interact with team mates and take part in the discussions as per the Focus points from the previous day. | It went relatively well and opened me up to speaking more freely without too much hesitation. | Now that I have familearised myself with the team it should become much easier to make significant improvements to the goal of improving communication | Initial attempt to be less hesitant was successful. I took up the role for presentation lead to further improve my communication skills by practiving and presenting the project later into the internship. | Continue improving by utilising opportunities to work on speaking with my peers. | N/A
|  | 10:25AM - 11:30AM | Client Meeting with Project Manager | This was the first time we met with the client where the current state, development goals, challenges and the future goal was laid out. Notes were taken and a few questions related to the internship were asked. | N/A | N/A | N/A | N/A | This meeting gave us a much clearer picture on what the client requires and the goals. It gave us some direction which was used in the next activity. | N/A | N/A
|  | 11:45AM | Scoping Document discussion and work stream selection | During this time we discussed the notes taken from the client meeting, some of the goals were clarified, some preliminary tasks were laid out and initial roles were selected. | During discussions I asked technical questions without providing any context. As I was the intern working on the technical aspect of the project I was told I should be able to speak with more clarity so it is easier to understand for everyone. | During discussions I was not able to frame my questions adequately for everyone to understand. After two attempts I was able to pose the questions I wanted. | Working with team mates required clear communication across departments which means communication must be understandable by everyone. | Now that I have identified another direction of improvement, I need to work on speaking more inclusively and clearly. | I was able to improve my communication significantly since Induction day by being more active in discussions. | integrate the advice received and attempt to speak and explain at a higher level without the unnecessary use of technical terms when speaking with peers from different streams, Project manager or client. | N/A
|  | 1:30PM | IT Meeting | After the previous discussion, we were split into two streams. The stream I worked on focused on the database mentioned by the client. The database is to be a repository of contacts comprised of agents for the AHH website and media groups. This was started off with a document that I created after discussion with my other two peers working in the same stream. This document was uploaded to a folder and used as the blueprint to create the two excel sheets containing the information. Various details such as Name / Contact Email / Address/ Location and more were tabulated in an organised and segmented manner. This is the initial database that will be used strictly by the administrator. This database will be expanded on, entries will be validated & refined and may be upscaled to a full application later. We were also given exactly 1.5 hours to complete this task and instruction was to regroup after the stream meeting. Because of this we split the work and each of the three of us worked on a specific portion of the task to make significant progress. | The progress was received well and some pointers and avenues of further improvement for the database was pointed out. Overall it was a success that gave us a good start to the internship | I was able to successfully execute my first task of creating a database of items requested. | From the feedback received it is clear I am able to efficiently work in a team working towards a goal. | Now that I have become much more comfertable with my peers, I will attempt to continue the work and produce artefacts for the upcoming client meeting on day 2. | Initial database was created and a large number of entries were made. I have also made noticeable improvement when communicating with outhers simply by being more conscious about what I say and ask. | Draft an initial report outlining progress and frame questions based on progress to continue work at the pace established. | Create prototype for database application before client meeting next Friday
|  | 3:00PM-3:15PM | IT meeting Brief | This was a short discussion with rest of the team on the progress achieved and some questions that had developed. | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | 3:15PM | IT Meeting #2 | This session just picked up the work from the previous session and continued to expand and polish the created databases | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | 4:05PM - 5:00PM | Project Manager Meeting | During this session the Project manager was presented with the work accomplished by both the streams. Task and role related topics were discussed and feedback on the overall goals were provided. A second meeting just for the IT team will be setup on Wednesday for discuss the technical aspects of the website and the needs of the client. | The feedback received from the project manager outlined our strenghts and weaknesses one of which was to change out thought process to approach a problem differently. Another Feedback provided was to provide examples with proposals to the client for a more definitive response. | Although the task went well the discussion had some deficiencies in terms of the lack of examples which led to some miscommunication | The lack of examples and miscommunication may cause issues later in the project so this will need to be resolved now. | Now that the problem has been identified I plan on bringing some real world example or a built prototype of some kind when proposing an option or alternative. This will not only assist in a clearer picture of the proposal but may also lead to an improvement to existing solutions. | This was the last item of Day 2 of the internship. Lot of progress was made and feedback is going to be integrated into the workflow from Day 3. | Asking questions to clarify database and website goals and usecases. Continuing work on teamwork, communication and IT skills. | Create prototype for database application, polish database to add lists, Write out progress report for client.
2021-11-10 | Extra Day | 6:00PM-8:00PM | Meeting with Jackson / Client for IT team member | This was the first time meeting Jackson, who is the developer of the website we will be working on. After the session on Tuesday I was placed on the sub-team that will be working on the website for the client. The goal for this meeting was to start setting up the development environment. | N/A | During the meeting we discussed the details of the tools we would require and how the development process works. As I was inexperienced I realized I would require substantial effort to make meaningful contribution to the project. | I decided to start learning the essential languages required and start setting up the enviormed outside of the allocated working days. | Working ahead of meetings helps speed up the process of getting up to speed. This should also segment the work across multiple days which will help with planning ahead and time management. | I was able to meet with both the Client as well as the developer where I got a much clearer picture of what my tasks were. | Drafting a timetable of upcoming tasks and deliverable dates will help in meetings when deciding what to work on. | Set up the development environment and have all nessary tools downloaded.
2021-11-12 | Day 3 | 9:00AM-9:30AM | Morning meeting with entire team | This was the first meeting of the day where the whole team provided updates, feedback and their tasks. After this meeting we split off into two streams where we worked on specific tasks. | During the meeting with the client I was speaking with the client to clear up some questions for the IT stream. I later received feedback from the supervisor to frame my question to be clearer and to provide options to the client to choose from to recieve clearer instructions. | During the day I worked on many different tasks and was able to make progress with one of the key deliverables. However it was difficult to get clear instructions from the client as the previous goals that had been laid out were shifted today. | Due to the shift we have to rethink the tasks and the timeline. To mitigate this from happening again I will need to approach the client for feedback on tasks in a different manner | Now that I have some experience working with a client and using my supervisor's feedback I have decided to build a prototype application for the client to examine during the next meeting. This should help with conveying the idea and getting a clear response. | We were able to get a clearer picture of the tasks that we would be required to do and have mapped a general timeline. We have also started work on the scoping document. Work on the first deliverable has started. | Have options and examples ready for the next client meeting | Continue working on the database, start work on scope document after meeting with jackson on Saturday.
|  | 9:30AM-11:00AM | IT stream | This session focused on getting all of the tools properly installed and fixing any errors in the installation process.
|  | 11:20AM-12:30PM | Client Feedback Meeting | During this meeting we got a better understanding of what the goal of the project would be, what our deliverables are and what the timeline would look like.
|  | 1:00PM - 2:00PM | Task allocation for the group | Here the whole group came together after the lunch break and discussed the client meeting. Specific tasks were assigned and we started to work on them.
|  | 2:00PM-4:00PM | Database Creation | After splitting off from the main team we started working on one of our deliverables which was the communications database. We decided to go with an excel sheet of information for now as it could later be migrated easily. We decided to create two spreadsheets instead of one to segment the tasks more effectively.
|  | 4:00PM-5:00PM | Final meeting for the day | Feedback was received on the work done and for the IT stream a third working day was allocated on Saturday where the members of the IT stream would work exclusively with Jackson and focus on the website.
2021-11-13 | Extra Day | 9:00AM-3:30PM | Meeting with Jackson | This day we started by setting up the environment first. We downloaded and made the database for the website (not communications database), downloaded git and linked accounts to the repositories, cloned the code and and installed all other nessary packages. After this we presented jackson with the feedback and listed out all of the other deliverables that we would produce in this placement. Tasks were assigned and we continued to work. At the end of the meeting we set a date for the next meeting and scheduled a feedback session on the progress we made. | N/A | Since our longer meetings with jackson happen once a week we do not get much time during the week to make major changes to the tasks and goals. | Due to the frequency of the meetings we are not able to implement any major changes during the week when feedback is received from the client | To tackle this we have decided to meet with jackson on Tuesdays after our regular working day to prepare for the next meeting during each week. | We made a lot of progress today and I now have specific tasks to focus on till the next meeting. We have also gotten our first draft for the scoping document. | Learning React / CSS / Javascript | Create the events section on the regional page of the website.
2021-11-15 | Extra Day | 11:00AM-2:30PM | Study session | This session focused on brushing up on React.js which is primarily used in the front end of the website. This is nessary as one of our deliverables is creating an events section. | N/A | I found react similar to other languages but the modular nature of the language was new and different to others. This made it a bit harded to get a grasp of the language | As this is one of the main focuses of the project, not being upto speed with react is getting in the way of progress. | As I get upto speed with react, I have decided I want to focus more on the back end of the project as one of my team mates is more comfortablewith the language than I am | I have gotten a much better understanding of the syntax and now able to understand the project files better. | The goal of learning the language still stays but the focus will now shift to javascript instead. | Create the events section on the regional page of the website.
0
2021-11-16 | Day 4 | 9:00AM-10:00AM | Morning meeting with the entire team and progress report | This was the daily progress report meeting. During this meeting we discussed the usual topics but also the peer presentation that would take place next week. | The main feedback received from the supervisor during the day was to approach an issue with alternatives ready and to request feedback frequently so that when plans change we can get started without a wait. | The plan for the IT stream has changed again. Due to the frequent changes the progress we make is not as valuable. | As this project is going at twice the speed of a regular project frequent changes affect us much more due to the lack of time making it harder to deliver on time. | To counter this issue we will focus on the fixed deliverable for now that is the communications database and a general events section and not just a christmas drive. | We were able to show the first draft of the events section and receive feedback on it. | Resume work on communications database | Start making a script for the peer presentation + tasks received from the client ahead of the next meeting.
|  | 10:00AM-11:00AM | Events section first draft | The IT stream was able to produce the first draft of the events section and show it to the supervisor and rest of the team. We were told to show it during the client meeting as well later during the day.
|  | 11:00AM -12:45PM | Client | This was the client meeting during which we demonstrated the draft. After the demo we received feedback and made a plan on how to incorporate those changes.
|  | 1:00PM-4:00PM | IT stream | During this session we worked to make the changes that were suggested. During this we were informed of another change that was to be made and refocused in that direction instead.
|  | 4:00-5:00PM | Final meeting of the day | During this meeting the supervisor was present and we decided to start working on the peer presentation as well and allocated tasks to make the presentation. I decided to become one of the presenters for the team.
|  | 6:00PM-8:30PM | Meeting with jackson | During this meeting we presented the scoping document that was drafted, a new design for the events section was made and tasks were assigned
0
2021-11-17 | Extra Day | 2:00PM-6:00PM | Learning Jsx and brushing up on javascript | This was a study session where I decided to learn the languages to better understand the project files and prepare for the the upcoming meeting on Friday and Saturday | N/A | Jsx is very similar to javascript but it also has elements of HTML in it. This was use extensively in the website files and so I decided to study it. | Doing this will help me read the files better and understand how to make changes myself | This will increase the speed at which we can make progress and changes as a team | I was able to get a usable grasp on both of them. I also started woring on the script for the presentation and revising the scoping document. | Resume work on communications database | Start mapping the path for the events section
0
2021-11-19 | Day 5 | 9:00AM:10:30AM | Morning meeting with the entire team and progress report | This was the first routine meeting of every working day where the entire team gives a progress report and assigns tasks for the day | I received a lot of feedback from the supervisor regarding my presentation performance. Although I did well I was asked to keep eye contact as much as possible with the camera and update the slides once the scope document was finalised | The presentation went well and I am working on the feedback but with another change in the project the scoping document has become larger than usual and will need to be confirmed. | Due to the size of the scope and this being a shorter placement I will need to finalise the scope document as well as the presentation | Due to the quickly developing nature of the project, I have decided to write the scope document in such a way that will require no changeseven with shifts to the project | I was able to finalise the script for the presentation and make good progress on the communications database. | Practice the presentation script and incorporate the feedback received from the supervisor | Finalise the presentation slides and the scope document
|  | 10:30AM-11:30AM | Client meeting | During this client meeting at first we were told the entire christmas drive would not be conducted which makes a large part of the project not usable. Hoever later it was clarified that it would go forward but only in certain regions which gave rise to another unique deliverable for the IT stream
|  | 11:30PM-1:00PM | Peer presentation practice | This session focused on practicing the script for the peer presentation with the other presenters.
|  | 1:30PM-4:00PM | IT stream | Here I decided to pick up on the communications database and resume adding to it again.
|  | 4:00PM-5:00PM | Final meeting of the day | During this meeting the IT stream was asked to verify the scoping document with jackson the next day as it seems larger than possible.
2021-11-20 | Extra Day | 9:00AM - 3:30PM | Meeting with Jackson | During this meeting we finalised the scoping document for the IT stream, fixed the pathing for the events section and started working on the queries file for the website. | N/A | The scope document is complete now after multiple changes | With the doucument being complete we now have a clear goal. | Having a fixed and clear goal gives us room to allocate tasks more freely and work more effectively as a team | The scope document is complete and now we have allocated tasks till next meeting. | Update the presentation slides | Split queries into smaller files that are segmented by subject
#NAME?
2021-11-22 | Extra Day | 11:00AM-4:00PM | Task For Tuesday | During this session I first updated the slides and the script for the peer presentation. I then started work on the queries file by splitting them into smaller files as per instruction. | N/A | I was able to clear two items and make good progress with the queries file. | Now that two major tasks are complete I can focus on just the website | As I am focused just on the website I was able to make a good amount of progress and will have more time for the upcoming meeting | The scope document is updated, script is complete and the task is being worked on. | N/A | Continue working on the Queries file
#NAME?
2021-11-23 | Day 6 | 9:00AM-10:00AM | Morning Meeting | During this meeting we discussed the progress made and what tasks we were going to work on. It was decided that we would practice the presentation during that day | Feedback from the supervisor during presentation practice was to make my script sound less like reading and more natural. | The timetable that I had created helped me stay on top of all of the work assigned to me. After using the feedback provided by the supervisor I was able to improve my presentation as well. | Having an organised work environment and applying the feedback received has made it much easier to perform well in the placement | Now that I am comfortable with my working environment I will be able to take on more work and produce a better result | Queries has beensegmented, work on making the controllers and the validation schemas are underway | Continue learning javascript | Complete the controllers that I had to finish. Finish the schemas before Saturday meeting.
|  | 10:00AM-11:30AM | Queries | During this session I worked on splitting queries into smaller segmented files in the controller folder for the website
|  | 11:30AM - 12:30PM | Presentation Practice | All of the presenters including myself went into a different meeting to practice for the peer presentation
|  | 1:00PM-5:00PM | Finalising Tasks | Here I worked on the website while the rest of the team focused on their own tasks and finished the scoping document. It was done on a single meeting so that there would be no need to jump channels for input.
|  | 6:00PM-9:00PM | Meeting with Jackson | During this meeting we started working on creating controllers for endpoints. I was allocated a set of the endpoints which I had to update but finished them early and decided to help my team mate with his while waiting for other tasks. After some explanation I was allocated another task of creating Schemas for validation.
#NAME?
2021-11-24 | Extra Day | 11:00AM-2:00PM | Javascript learning | This was a short session dedicated to learning javascript for upcoming tasks as I have taken up the role to work on the back end of the website | N/A | Learning the language has gotten much easier than before with a lot of practice. | As it is easier than before I am now able to explore outside of the logic that I am presented with in the website files. | Due to this I am able to implement and try different solutions which will help expand my knowledge base | A round of practice for the peer presentation, all controllers have been created. |  | Complete making the validation schemas
|  | 7:00OM-9:00PM | Pressentation Practice and tasks | Here first I worked on rehearsing the script for the presentation and then went back to completing the tasks for Saturday.
2021-11-25 | Peer Presentation | 9:00AM-10:10AM | Peer Presentation | We were the second group to present and it went well with good feedback for our slides, transitions and timing. | N/A | The presentation went much better than expected and I performed better than I had in the practice sessions | Our team received positive feedback for our performance | This was a confirmation that my communication skill has improved significantly since I started the placement | Peer presentation is now over. My communication skill has improved a lot. | N/A | N/A
26/11//2021 | Day 7 | 9:00AM-5:00PM | General Meeting | The supervisor for the project gave the members of the IT stream a day off as we have been putting in a lot more extra time than is required due to the work load. I still decided to join in the meeting with the Brand stream to help out where I can while completing my own tasks in the back ground for the meeting on saturday. During this meeting we started work on the final report and I was assigned the role of completing the portion for the IT stream. | N/A | N/A | N/A | N/A | Started work on the final report. Finished making all of the validation schemas. | N/A | Complete the final report draft before Tuesday meeting.
2021-11-27 | Extra Day | 9:00AM-3:10PM | Meeting with Jackson | During this meeting I was told that the christmas drive would need to be ready 2 weeks ahead of time. Because of this we decided to drop everything else and focus just on that. I used the validation schemas to bering functionality to the organization controller. After this there was a very long debugging session where the meeting ended with my task being to try and fix the error ahead of the tuesday meeting. | N/A | I was able to work on my own without any support but I was not able to debug as easily. | This means I am able to write code and understand the logic but I am not able to follow it closely enough to identify where the error may be. | Now that I have identified one more of my weaknesses it will be a personal goal to make improvement in this area as well. | Schemas are ready and wrok on integrating them with the controllers have started | Learn how to debug effectively | Fix errors in the organization controller before Tuesday.